Residential-Yard Opening — Implementation Backing Note

International evidence for the dedicated feasibility/implementation study referenced in Output 10. Internal project-file note — not part of Output 8 or Output 10.

| Status | Backing note / study seed — illustrative, not a recommendation |
| --- | --- |
| Relation to deliverables | Output 10 names a few cases and the candidate organisational models, then defers the mechanism here. This note must NOT be read back into O10 as a committed plan. |
| Evidence basis | NotebookLM 'Yerevan notebook' synthesis + an adversarially cross-checked precedent-research pass; conflicts between them are flagged, not averaged. |
| Bottom line | A marginal-supply tool worth piloting, not a structural fix — and genuinely untested in a post-Soviet courtyard context. |

1. Reality check — read this before the optimistic material

The international literature shows the planning logic is settled (daytime residential vacancy coincides with commercial peaks) and the technology is off-the-shelf (app booking, ANPR gating). The binding constraint everywhere is the governance / consent / land-title layer — and in the post-Soviet case it is compounded by unresolved courtyard ownership and a resident default of gating yards to keep outsiders out.

Novelty. There is no well-documented case of a post-Soviet residents' association running a paid public-parking operation in its own gated courtyard. The concept is genuinely novel here.

Counter-trend. Kyiv floated charging for courtyard parking and shelved it under public backlash, tripped up by ownership ambiguity. Moscow and Tbilisi subsidise/install courtyard barriers to exclude outsiders. The demonstrated post-Soviet impulse is exclusion, not sharing.

Success condition. Schemes succeed where residents voluntarily rent their own surplus for their own revenue; they fail where the programme is perceived as taking from residents (top-down charging) or as self-dealing by an association board.

Caveat. Treat courtyard-sharing as a marginal-supply and demand-management tool, not as the structural fix for the BRT-displacement deficit. Even showcase cases report aspirational utilisation targets and owner earnings often too small to motivate participation.

2. International cases (transferable elements)

| Case | Model type | Most transferable element | Evidence quality |
| --- | --- | --- | --- |
| Stockholm Parkering (SE) | City-owned intermediary | City-backed company bridging private lots and demand; satisfies developer parking needs without new build | Documented (municipal) |
| Vancouver West End (CA) | Municipal price alignment | On-street permit price set at off-street market rate so cars move into under-used parkades | Modelled outcomes; policy documented |
| Hangzhou 邻里停 (CN) | Platform + revenue split | Revenue split owner / owners' committee / management — association becomes a paid partner | Gov-sourced; uptake modest |
| Beijing staggered (CN) | Policy + enforcement tech | Time-staggered sharing principle; ANPR / app | Headline counts weighted to commercial/gov lots — see caveat |
| JustPark / Akippa / Share with Oscar | P2P platforms (UK/JP/AU) | Trust machinery: insurance, address privacy, tax allowance, easements | Vendor-sourced revenue figures |
| King County Metro (US) | Shared-parking lease agreements | Leasing residential/church spaces for Park & Ride; statutory impoundment for overstay | Documented (transit agency) |
| Stockholm / ParqEx / WhereiPark | Whole-building monetisation | Board-controlled opening of surplus building spaces with tiered commission + ANPR | Vendor case studies (proof-of-concept) |

Caveat. Beijing's widely-cited ~28,000 shared spaces / 330 lots is largely COMMERCIAL and GOVERNMENT lots, and partly the reverse direction (residents renting overnight in commercial lots) — not day-into-residential-courtyard at scale. Do not present it as a like-for-like Yerevan analogue. Social-credit-linked enforcement is noted in the source but is not an appropriate model to cite approvingly.

3. Candidate organisational models (the choice the study must make)

| Model | Who leads | Mechanism | Trade-off |
| --- | --- | --- | --- |
| Public / state-agency-led | Municipal parking authority or PCS; or a dedicated city-owned company (Stockholm Parkering model) | City brokers, leases and enforces; association consents and is paid | Clear accountability; carries top-down political risk (Kyiv) |
| Public-private partnership | Licensed operator or parking platform under a municipal framework | Operator runs booking/access/payment; revenue shared with association | Fast to stand up; depends on a credible operator and a clean revenue split |
| Association-led, city-enabled | The hamatirutyun itself, under a municipal template | Association opens and manages its courtyard; light regulation + standard agreement | Highest consent legitimacy; weakest guarantee of dependable public capacity |
| Combination | City framework + PPP operator + association consent | Layered: enabling regulation, operator, paid association, revenue-back district | Most robust on the evidence; most moving parts |

4. Load-bearing preconditions the study must resolve

Land title. Who legally owns each courtyard (municipality / hamatirutyun / unregistered). This determines who may authorise the arrangement and retain revenue — and is the failure point in every post-Soviet case.

Association capacity. Whether the hamatirutyun is recognised as a contracting entity able to execute a shared-parking agreement on behalf of owners, and the consent procedure / vote threshold under Armenian condominium law (the owners' meeting is the supreme management body).

Tax & insurance. Tax treatment of association parking income (in the US, non-member parking income is taxable / UBIT; verify the Armenian position — do not assume tax-free), and whether commercial/public use voids residential insurance cover.

Durability. A legal instrument that survives a board change or property sale (covenant running with the land; the Dutch 'qualitative obligation'; the UK 'deed of easement').

Inventory & data. Complete the geo-referenced on-street (red/blue-line) inventory first, so yard capacity is mapped to where it most efficiently replaces removed kerb; define an open data standard so yard availability can feed the city app.

5. De-risking machinery observed elsewhere

| Risk | Mechanism used elsewhere |
| --- | --- |
| Resident security anxiety | Address privacy until booking confirmed (Share with Oscar); visible ANPR |
| Overstay blocking residents | Time-boxed digital passes; statutory impoundment (US RCW 46.55); ground locks (Beijing) — heavy-handed, weigh carefully |
| Vehicle-damage liability | Dedicated parking-sharing insurance co-developed with insurers (Akippa + Sompo) |
| Owner inertia / 'untouchable asset' | Revenue-back to the courtyard (participatory budgeting, Vancouver; parking benefit district, Shoup) |
| Weak financial incentive | Hangzhou owner/association/management split; UK tax-free allowance on rental income |
| Platform fragmentation | Mandate open-API integration into one city dashboard |

6. Indicative phasing (illustrative — for the study to test, not a commitment)

Sequencing should follow the international experience that single-owner institutional and commercial lots open far more readily than residential courtyards and should be activated first.

Phase 1 (pilot). Anchor on willing institutional/commercial lots; pilot 3–5 willing building associations in a high-sensitivity zone using existing PCS ANPR; price daytime yard access at parity with adjacent blue-line rates; evaluate uptake, conflict rate and revenue at 6 months.

Phase 2 (expansion). Integrate yard availability into the PCS app; stand up an association registration framework with standardised agreements; map further courtyard supply.

Phase 3 (maturity). Move from resident-exemption pricing toward demand-responsive pricing across on- and off-street supply; fold revenue into a neighbourhood-governed benefit district.

7. Source caveats

The NotebookLM synthesis is uniformly optimistic and omits the post-Soviet counter-trend; this note restores it.

Revenue and scale figures from platforms (JustPark, Spacer, ParqEx, WhereiPark, Akippa) are vendor-sourced proof-of-concept, not independently audited.

Vancouver (88%→60%) and Beijing (20–40% supply reduction; 7.3 Mt CO₂) figures are MODELLED scenarios, not realised outcomes — do not quote as Yerevan facts.

No ITDP/World Bank/GIZ study specific to Yerevan or Tbilisi courtyard-sharing was located; the topic is under-documented for this context, which is itself a reason to commission the study.