Yerevan Parking Study  •  Internal Review Memo

Mitigation Measures — Audit & Validation against the Field Survey

Pressure-testing the Output 8 and Output 10 mitigation measures — drafted a priori, before fieldwork — against the field-survey evidence.

Scope. Re-derived independently from the source deliverables and the field-survey dataset; convergence and divergence with the report's existing “Implications” chapter are flagged. Figures are from the validated survey run (six areas; 208 on-street segments; ~2,930 marked spaces) and the raw stay-length histogram (11,394 on-street stays).

1.  Decision

The measure menu holds up. The measure targeting does not.

Nothing in the survey justifies deleting a measure. But the survey overturns three things that were guessed before fieldwork:

ELEVATE & COMMIT — the off-street measure (M7 — open residential yards). The entire displacement case rests on off-street capacity: surviving on-street absorbs only 43% of peak displaced demand (14% in the Kentron core, 0% in Komitas), and 92% of the off-street capacity that closes the gap to ~100% is gated residential yards counted at gross capacity as if already open. So the “demand can be re-absorbed” headline is silently conditional on opening those yards — i.e. on M7. Yet O10 frames M7 as an optional pilot in the lower-sensitivity zones. It is the load-bearing measure of the whole strategy and must be made a committed precondition, led in the core. No net-new measure — M7 elevated.

RE-SCOPE (misdirected) — visitor caps / maximum-stay limits — but keep them. Their logic (evict long-stay commuters) is contradicted by the data: ~63% of stays are ≤1h, ~77% ≤2h, the overnight (8h+) share is ~7% — and those are residents (permit-exempt), while genuine daytime all-day workers (5–8h) are only ~6%; turnover is already 5–11 vehicles/space/day. A 2-hour cap would mostly bite 3–4h errand visitors, not commuters. Do not remove — demote to a targeted contingency for specific low-turnover spots, and lead with pricing.

RE-ALLOCATE — measures across the sensitivity zones. The high-sensitivity (Kentron) package is curb-led, but the data shows curb cannot absorb there. Yard-opening (M7) — now assigned to lower-sensitivity zones — belongs first in the core (Kentron is 86% yard-dependent, Komitas 100%). Komitas, classed Medium, behaves like High (123% peak, 0% on-street absorption); Shiraz behaves like Lower (75% peak, 69% absorption). Targeting must follow measured behaviour, not a-priori geography.

Net: sufficient as a toolkit — no net-new measure. Re-scope caps (demote, lead with pricing), elevate and commit M7 (the off-street measure the headline depends on), and re-allocate by zone. The “corridor itself = primary mitigation” premise is empirically confirmed — peak displaced demand is only 55% of spaces removed (908 cars vs 1,643 spaces).

Independent corroboration. Setting the report's existing “Implications” chapter aside and re-deriving, I reach the same Kentron curb→off-street recalibration and the same Gai Avenue residual-risk flag. I go further on three points it does not make: the off-street headline is conditional on opening gated yards (M7) and must say so; visitor caps are misdirected on the measured data; and the displaced-demand peak is midday in every area (so daytime yard availability aligns). Neither contradicts the existing recommendations.

2.  Inventory of current measures

Output 8 sets up the displacement frame (supply inventory, absorptive-capacity pools, sensitivity zones). The measures themselves live in Output 10.

| # | Measure | Stated purpose | Zone(s) |
| --- | --- | --- | --- |
| M0 | The corridor itself (modal shift via BRT) | Primary mitigation | All |
| M1 | Extend paid zones (red/blue ≤100 m) | Absorb spillover; manage demand | High + Med |
| M2 | Delivery / loading bays | Protect commercial servicing | High + Med |
| M3 | Visitor caps (max-stay) | Increase turnover | High |
| M4 | Resident permits (transitional) | Protect residents from spillover cost | High |
| M5 | Organise free parking (no pricing) | Structure chaotic free supply | Lower |
| M6 | Park & ride | Intercept inbound commuters | Med + Lower |
| M7 | Open residential yards | Create off-street supply | Lower |
| M8 | ANPR enforcement extension | Enabling | Cross-cutting |
| M9 | Duration-based fines | Deter long storage | Cross-cutting |
| M10 | Revenue earmarking | Public legitimacy | Cross-cutting |
| — | Phasing + monitoring | Sequencing (before removal) | All |

3.  Validation against the survey

Verdicts: ✓ confirmed  ·  ◆ re-scope  ·  ○ cannot test (keep on precaution).

| Measure | Verdict | What the data says |
| --- | --- | --- |
| M0 Corridor / modal shift | ✓ Confirmed | Peak displaced demand 908 vs 1,643 removed = 55%. The “displaced < removed” principle is now locally measured (was European precedent only). Avg 43% vs peak 93% → don't replace 1:1. |
| M1 Extend paid zones | ◆ Re-scope | Right lever (90% of kerb unpriced; peaks 93–138%). But its O10 purpose is “absorb on side streets” — and the core has no spare side-street capacity (Kentron 14%, Komitas 0%). In the core it is a demand-rationing tool, not absorption. |
| M2 Delivery bays | ✓ (inferred) | No direct freight count, but ≤1h dominance (~63%) + very high turnover implies heavy short-access. Keep; rests on inference, not measurement. |
| M3 Visitor caps / max-stay | ◆ Re-scope, not remove | Overnight ~7% (1h-rule; residents, permit-exempt); daytime all-day (5–8h) only ~6%; ≤1h ~63%; turnover already 5–11/day. A 2h cap mostly bites 3–4h errand visitors, not commuters. KEEP but demote to a targeted contingency for low-turnover spots; lead with pricing. |
| M4 Resident permits | ○ Cannot test — keep | Daytime window still misses true overnight storage; the overnight band (now ~7% via the 1h rule) is a floor and must NOT be used to weaken this. Keep, justified by land-use, not survey data. |
| M5 Organise free parking | ✓ Confirmed | O8: 87.6% unmarked, 79.9% unsigned; ~90% of kerb free. Lower-pressure areas (Malatia 54%, Shiraz 75% peak) have headroom — structure before pricing. (Also needed in Kentron — see G5.) |
| M6 Park & ride | ◆ Weak support | Premise = intercept commuters, but the daytime fleet is overwhelmingly short-stay, weakening the “many commuters to intercept” assumption within these areas. Keep as a study item; don't oversell. |
| M7 Open residential yards | ✓ Load-bearing + under-committed | 92% of off-street absorption is gated residential yards (1,778 of 1,935 spaces); the ~100% headline is conditional on opening them. M7 is load-bearing (Kentron 86% yard-dependent, Komitas 100%), yet O10 makes it an optional lower-zone pilot. Elevate to a committed core precondition. |
| M8 ANPR enforcement | ✓ Enabling | Necessary for every priced measure. Keep. |
| M9 Duration-based fines | ○ Keep, don't oversell | Same caveat as M3: daytime fleet isn't long-stay. Value is overnight storage (unmeasured) + system maturation. |
| M10 Revenue earmarking | — Out of scope | Political-legitimacy measure; survey neither supports nor refutes. Keep. |
| Phasing | ✓ Reinforced | “Mitigation before removal” matters more given the off-street dependency — the gated yards (M7) must be opened and the pricing in place before the kerb goes. |

4.  Gaps the survey revealed

| Gap | Why it's only visible now | In current set? |
| --- | --- | --- |
| G1 — Absorption hinges on opening gated yards (M7) | 92% of the off-street capacity that closes the gap is gated residential yards, counted at gross capacity as if already open; on-street alone covers 43% (14%/0% in core). The ~100% headline is conditional on M7, which O10 treats as optional. | Re-scope M7 — commit it |
| G2 — Gai Avenue local shortfall | Only area where gross best-case capacity (89%) < peak demand. Gai isn't in O10's zone lists. | No — targeted |
| G3 — All-day, zone-wide saturation in core | Kentron: 89% of zones >85%, high all working day (peak hour 21:00). | Partial — scope |
| G4 — Evening occupancy peak under-captured | Kentron's 21:00 / Malatia's 18:00 occupancy peaks are driven by retained residential streets the daytime window only partly sees. (Displaced demand itself peaks midday — yard timing is fine.) | Partial — informs M4 |
| G5 — Worst informal layout is in the core | Kentron kerb ~60% angled/informal. M5 (organise) is assigned only to lower zones. | Mis-assigned |
| G6 — Komitas mis-classed Medium | 123% peak, 0% on-street absorption — behaves like High; Medium package won't fit. | No — re-class |

5.  Fact → measure mapping

Hard, data-driven justifications for the retained / correct measures — a sourcing map for later wiring into the reports.

| Survey fact (measured) | Justifies |
| --- | --- |
| Peak displaced demand 908 vs 1,643 removed (55%) | M0; “no 1:1 replacement”; O8 quantification; O10 court-defensibility |
| Avg 43% vs peak 93% occupancy citywide | M1/M3 framed as peak-demand management, not supply expansion |
| ~90% of kerb unpriced (2,654 white vs 276 blue); 87.6% unmarked | M5 organise free; M1 extend paid |
| Kentron peak 138% / on-street absorption 14%; Komitas 123% / 0% | High-zone package must be off-street-led, not curb-led |
| 92% of off-street absorption is gated residential yards (1,778 / 1,935 spaces) | M7 is the load-bearing precondition — elevate & commit; the ~100% headline depends on it |
| Off-street carries 86% of Kentron's absorption, 100% of Komitas's (on-street 14% / 0%) | M7 most critical in the core — re-allocate it up from the lower zones |
| Displaced demand peaks midday (10:00–15:00) in every area, incl. Kentron/Malatia | Daytime yard availability aligns with the displaced peak — supports M7 timing |
| Stay mix ~63% ≤1h / ~77% ≤2h / ~7% overnight 8h+ (1h-rule); turnover 5–11/day | Pricing-for-turnover (M1) as headline; M3 caps demoted to targeted |
| Gai Avenue total absorption 89% (<100%); no nearby residential yards to open | G2 targeted provision at Gai — M7 cannot rescue it |
| Kentron 89% of zones >85%, all-day | All-day, zone-wide enforcement hours (G3) |
| Kentron / Malatia evening occupancy peak (retained residential) | M4 resident permits; review paid-hours window (G4) |
| Malatia 54% peak / 97% absorption; Shiraz 75% / 69% | Light-touch (M5/M7) confirmed for genuine lower-sensitivity areas |

6.  Critique of the user grouping

Current grouping (your directive, in compute_field_survey_metrics.mjs → STAY_BIN, shown in StoryStep.svelte): duration-of-stay, three ways — Visitor <2h / Commuter 2–8h / Long >8h, where “duration” = number of distinct hours a plate is seen.

What the data looks like (11,394 on-street stays, with the approved 1-hour overnight correction applied — see §A):

1h               62.8%  █████████████████████████████████████████████

2h               14.4%  ██████████

3h                6.5%  █████

4h                3.5%  ██

5h                2.2%  ██

6h                1.6%  █

7h                1.2%  █

8h                0.9%  █

8h+ / overnight   6.9%  █████

The 1h–8h bars are a smooth decay with no natural breakpoint; the overnight bucket holds the edge-only stays reclassified by the approved rule.

Findings:

The distribution is a smooth decay — any boundary is arbitrary. The split was a label imposed on continuous data, not derived from it.

“Visitor <2h” is really “seen in a single hourly sweep.” Integer-hour resolution: <2h = exactly 1h = ~63%. It can't tell a 5-minute drop-off from a 55-minute stay.

“Commuter 2–8h” conflates two behaviours: the 2–4h errand/shopper (~24%) and the 5–8h worker (~6%) — opposite policy responses (turnover pricing vs. interception).

The overnight band is now modelled, not an artifact. The approved 1-hour rule lifts the 8h+ band from an observed 1.7% to ~6.9% by reclassifying edge-only stays as overnight. Even so it stays a floor — the daytime window (07:00–24:00) still cannot see genuine overnight storage, so it must not be used to weaken the resident-permit case.

It doesn't match the deliverables' own user groups. Output 10's “Impacts on Specific User Groups” is purpose-based — residents, customers, commuters, delivery, taxi, persons with disabilities — which is what the measures actually serve.

Recommendation — adopted approach

Keep the three-way duration split, with the overnight band populated by the approved 1-hour boundary rule. This resolves the worst problem — the previously empty, mislabelled long band now carries a measured overnight share. Working basis: ~63% visitor (<2h) / ~30% commuter (2–8h) / ~7% overnight (8h+).

Two residual cautions. (a) The visitor/commuter boundary still sits on a smooth decay with no natural gap, so treat the split as descriptive, not categorical. (b) For the mitigation mapping, anchor measures to purpose-based user groups (Resident, Visitor/Customer, Commuter/Worker, Delivery, Taxi, PwD) and use the duration data as evidence of population size, not as the grouping itself.

7.  Measures → groups (recommended grouping)

| User group (purpose-based) | Survey signal | Mitigation measure(s) |
| --- | --- | --- |
| Visitors / customers (~77% ≤2h turnover demand) | ~63% ≤1h; turnover 5–11/day | M1 pricing-for-turnover (headline); M5 organise free; M2 delivery bays |
| Commuters / workers (~6% daytime all-day) | 5–8h stays; small but present | M6 park & ride; M9 duration-based fines / price differential; M3 caps marginal |
| Residents (overnight ~7%, 1h-rule) | Daytime window undercounts; evening occupancy peaks | M4 resident permits; M7 open yards (load-bearing). Never M3 caps |
| Delivery / freight | Inferred (short-access + turnover) | M2 loading bays; grace period |
| Taxi | In inventory | Designated taxi stands (design) |
| Persons with disabilities | Statutory | Retained accessible bays (design) |

8.  Caveats binding every conclusion

Daytime window (07:00–~24:00). Overnight residential storage is structurally invisible — resident permits, duration-based fines, and the “long-stay” band cannot be tested and must not be weakened on this data.

Six areas, not the full corridor. A demand overlay (208 segments, ~2,930 spaces), not the 8,862-space inventory. Absorption is gross best-case (every nearby space available, drivers willing to go off-street); real-world friction tightens every balance.

Duration = distinct hours observed, not continuous dwell or vehicle type — coarse, and silent on freight/taxi/PwD purpose.

Bottom line. The a-priori menu was sound; the survey doesn't break it, it re-aims it — no net-new measure. Elevate and commit M7 (open residential yards), the off-street measure the absorption headline silently depends on; demote max-stay caps in favour of pricing (keep, don't remove); push the off-street and organisation measures up into the saturated core; and fix the Komitas (Medium→High) and Gai (unclassified→targeted) zone assignments. The grouping keeps its three-way duration split — now with the overnight band populated by the approved 1-hour rule — while the mitigation mapping is anchored to purpose-based user groups.